# Hospital Modernization
Student MVP Project

6-Week University Project | 5 Students | 4 Development Weeks

Project Platform: www.exploreN2P.com

PROJECT GOAL Build a working prototype that demonstrates one complete patient journey from registration to doctor-approved notes and a lab or prescription order.

Dummy/synthetic patient data only.

# Project Scope

The prototype follows the hospital workflow shown in the provided modernization diagram: patient registration, queue management, nurse intake, doctor consultation, laboratory/pharmacy orders, record storage, and patient information access.

## Final MVP Flow

Patient Signup  →  Queue  →  Nurse Intake  →  Doctor Consultation  →  Voice Note  →  AI Rewrite  →  Doctor Approval  →  Lab/Prescription Order

# The 5 Development Steps

## 1. Patient Signup + Queue

Create a simple web form for a dummy patient and place the patient into a queue.

Patient registration form

Patient queue/status screen

Basic desktop/web notification

## 2. Nurse Intake + Patient Record

Create the patient record used by the clinical team.

Enter vitals and basic patient information

Enter insurance/administrative details

Upload sample medical reports

## 3. Doctor Consultation + Voice AI

Allow the doctor to review the patient record and create consultation notes by voice.

Record doctor dictation

Convert voice to text

AI organizes/re-writes the note

Doctor edits and reviews the note

Doctor approves the final note

Store: raw material/transcript, doctor-edited version, final approved version

## 4. Prescription + Lab Order

Allow the doctor to create a prescription or diagnostic test request.

Create prescription order

Create lab/test order

Simulate sending the order

Store order and status in the patient record

## 5. Integration + Final Demo

Connect all modules into one working patient journey and prepare the handover.

End-to-end testing

Fix major issues

Final demonstration

Short technical documentation

Source-code and setup handover

# 5-Student Work Assignment

| Student | Primary Area | Main Responsibility |
| --- | --- | --- |
| Student 1 | Patient + Queue | Signup, patient queue, status screen |
| Student 2 | Nurse + Records | Vitals, intake, document upload |
| Student 3 | Doctor UI | Doctor dashboard and consultation workflow |
| Student 4 | Voice AI | Voice-to-text, AI rewrite, edit/approval flow |
| Student 5 | Orders + Integration | Prescription/lab order, integration and testing |

# 6-Week Schedule

| Week | Focus | Expected Output |
| --- | --- | --- |
| Week 1 | Introduction + planning | Access, requirements, design, task assignment |
| Week 2 | Build Sprint 1 | Patient signup, queue, nurse intake |
| Week 3 | Build Sprint 2 | Doctor dashboard + patient record |
| Week 4 | Build Sprint 3 | Voice AI + doctor approval |
| Week 5 | Build Sprint 4 | Lab/prescription orders + full integration |
| Week 6 | Documentation + final demo | Testing, handover, final presentation |

# Student Rules

Use only dummy/synthetic patient data.

Keep the prototype simple and working; avoid unnecessary features.

All project access, testing, boards, and documents will be managed through www.exploreN2P.com.

Integrate work continuously; do not build five separate applications.

AI scope in this phase is limited to doctor voice documentation and rewriting.

AI diagnosis, scan analysis, blood-work analysis, and clinical recommendations are future phases.

# Final Acceptance Criteria

A dummy patient can register and enter the queue.

A nurse can enter vitals and upload a sample report.

A doctor can open and review the patient record.

The doctor can dictate a note and receive voice-to-text output.

AI can organize/rewrite the dictated note.

The doctor can edit and approve the final note.

The required note versions are saved in the patient record.

The doctor can create and send a simulated prescription or lab order.

The complete workflow can be demonstrated from start to finish.

# Future Phase - Not Part of This Student MVP

Future versions may analyze the patient's history, blood-work results, scan reports, and other clinical information. These capabilities are intentionally excluded from this six-week project.

Reference: Hospital Modernization workflow diagram supplied for this project.